## Tasks
Story ID | Title | Valid from | Estimate | Is done? | Work done | Comment
K726 | Set up development environment | 2017-10-09 | 3 | 1 | 3 | Done by Everyone
K726 | Research Neural Nets | 2017-10-09 | 3 | 1 | 3 | Done by Madeline & Megan
K727 | Readme on existing ML | 2017-10-09 | 3 | 1 | 3 | Done by Jose
K727 | Front end interface | 2017-10-09 | 5.5 | 1 | 5.5 | Done by Harland
K728 | Create Neural Net | 2017-10-09 | 8 |  | 2 | Push to Sprint 2
K729 | Preprocess Data for Usuable Matrix | 2017-10-09 | 3 |  | 0 | Push to Sprint 2
K729 | Tie Backend and Frontend | 2017-10-09 | 2 |  | 0 | Push to Sprint 2
K729 | Tweak Neural Net | 2017-10-09 | 2 | 0 | 0 | Push to Sprint 2

## Burn-up
Date | Scope | Work done
2017-10-10 | 29.5 | 1
2017-10-11 | 29.5 | 1
2017-10-12 | 29.5 | 1
2017-10-13 | 29.5 | 3
2017-10-14 | 29.5 | 3
2017-10-15 | 29.5 | 6
2017-10-16 | 29.5 | 8
2017-10-17 | 29.5 | 11
2017-10-18 | 29.5 | 13
2017-10-19 | 29.5 | 15
2017-10-20 | 16.5 | 16.5